## Guidance Notes
Guidance Notes
1. The 'master list' is provided to give a consistent basis for all Drain London SWMP Action Plans
2. Populate all fields where data is available (dropdown menus are provided where relevant)
3. The 'MasterList' tab should be retained as a minimum within this spreadsheet and delivered to the LB (as an excel spreadsheet)
4. Extra tabs can be added to this spreadsheet to create summary tables as per the requirements of the individual LB - but should be dynamically linked back to the master list
(e.g. sorted by lead organisation, action type or other combination of fields)
5. Action Plan tables presented in the main SWMP Report text can be made up of any subset of the fields included in the Master List and sorted / categorised as per individual LB requirements
6. No formatting restrictions are placed on this spreadsheet - column widths, colours, field order and text style can be varied as required.
7. No editing of field headers or dropdown menus is permitted.
Action Types' are defined as follows:
Action Type Abbreviation | Definition | Explanation
FWMA / FRR | Flood and Water Management Act / Flood Risk Regulations | Duties and actions as required by the FRR and FWMA - Refer to Appendix A of the LGG 'Preliminary Framework to assist the development of the Local Strategy for Flood Risk Management' (February 2011) for minimum requirements
Policy | Policy Action | Spatial planning or development control actions
C + M | Communication / Partnerships | Actions to communicate risk internally or externally to LLFA or create / improve flood risk related partnerships
F + R | Financial / Resourcing | Actions to secure funding internally / externally to support works or additional resources to deliver actions
I / F / D | Investigation / Fesibility / Desgin | Further investigation / feasibility study / Design of mitigation
FMA | Flooding Mitigation Action | Maintenance or capital works undertaken to mitigate flood risk

## MasterList
ID | Action |  |  | Priority Ranking | Cost |  |  | Benefit | Potential Funding Source | Timing |  |  | Action Type | Comments | Responsibility |  |  | Other Stakeholders | EU Related? | Review |  | Location |  | Linkages
| What? | How? | Where? |  | Investigation / Feasibility | Capital | Other |  |  | Timeframe | Start Date | Approx. Duration |  |  | Lead Organisation | LLFA Dept. | Primary Support |  |  | Frequency | Next Review Date | CDA ID | Policy Area ID | LB Action IDs related? | Neighbouring LB Action IDs related?
1 | Take forward existing and future local actions in the SWMP | Continue to run a Flood Working Group of Council officers and Environment Agency Rep meeting twice a year | Borough-wide | High | - | - | - | Co-ordinated delivery of local flood risk management within the borough | LB only | Short | 2011 | Short | FWMA / FRR | The flood group includes officers from Planning, Transportation and highways, Emergency Planning, Building Control from within the council and reps from EA. It meets quarterly and minutes are taken | LB Tower Hamlets | Transport / Highways | Other members of working Group | Environment Agency | No | Annually | 2015-03-01 | N/A
2 | Take forward strategic existing and future actions in the SWMP that involve multiple boroughs or other flood risk management authorities | Continue to attend 'Drain London Group 4' working group and spin-off working parties | Sub-regional | High | - | - | - | Co-ordinated delivery of local flood risk management across the region | LB only | Short | 2011 | Short | C + M | Members of the flood team attend Drain London Group 4 meetings | LB Tower Hamlets | Transport / Highways | Other Group 4 Boroughs | Environment Agency, Thames Water, TfL, Network Rail | No | Annually | 2015-03-01 | N/A
3 | Develop, maintain, apply and monitor a Strategy for local flood risk management of the area. | Use the outcomes of the SWMP as the first stage of preparing a strategy. Refer to Preliminary Framework to assist the development of the Local Strategy for Flood Risk Management ‘A Living Document’, February 2011, Local Government Association. | Borough-wide | Low | - | - | £20K | Meeting obligations under the Floods and Water Management Act | LB only | Medium | 2013 | Short | FWMA / FRR | Work started in mid 2013 and the document is in modular and electronic format - it wil link to other documents held electronically and updated regularly. The consultation draft was completed in October 2014 and permission is being sought to consult. The document should be published on-line in January 2015 | LB Tower Hamlets | Transport / Highways | Environment Agency |  | No | Annually | 2015-03-01 | N/A
4 | Prepare a PFRA in relation to flooding in the LLFA’s area. | Use the PFRA developed for Drain London as the basis for the next round of PFRAs in 2017 | Borough-wide | Low | - | - | £3K | Meeting obligations under the Flood Risk Regulations | LB only | Long | 2017 | Short | FWMA / FRR | unallocated yet | LB Tower Hamlets | Transport / Highways | Environment Agency |  | Floods Directive | Every six years | 2017 | N/A
5 | Prepare flood hazard maps and flood risk maps | In relation to each identified area of significant risk, a flood hazard map and a flood risk map need to be produced. The Drain London model results may be used as a starting point. Refer to Preliminary Framework to assist the development of the Local Strategy for Flood Risk Management ‘A Living Document’, February 2011, Local Government Association. | Borough-wide | Medium | - | - | £5K | Meeting obligations under the Flood Risk Regulations | LB only | Medium | 2013 | Short | FWMA / FRR | Environment Agency has created and published Risk and Hazard plans for all London LBs. We checked the website and it looked ok at the time it was created. However, since we have had the impact of rainfall on LBTH remodelled, the flooding situation is looking quite different. Some reworking will be needed when that information is finalised. This should be done before the end of 2014 | LB Tower Hamlets | Transport / Highways | Environment Agency |  | Floods Directive | Annually | 2015-03-01 | N/A
6 | Prepare flood risk management plans | A LLFA must prepare a flood risk management plan for each area of significant risk. | Borough-wide | Low | - | - | £20K | Meeting obligations under the Flood Risk Regulations | LB only | Medium | 2014 | Short | FWMA / FRR | We plan to contribute to one that will be lead by EA. | LB Tower Hamlets | Transport / Highways | Environment Agency |  | Floods Directive | Every four years | 2014 | N/A
7 | Co-operation - Authorities must co-operate with each other in exercising functions under both the Act and the Regulations. | Regular sharing of data and expertise in addressing local flooding issues | Borough-wide | High | - | - | - | Meeting obligations under the Floods and Water Management Act | LB only | Short | 2011 | Long | FWMA / FRR | Flood team met with TW to discuss the modelling of flooding including sewerage. TW said they don’t clean sewers unless there is a problem. Subsequently they explained that they are beginning to model the function of the sewerage and predict water levels. They are monitoring these against measured values to check that the network is operating properly and not blocked. This doesnt seem to be progressing fast. Floods in September appear to have been caused by blocked sewers. | LB Tower Hamlets | Transport / Highways | Environment Agency, Thames Water | TfL, Network Rail | No | Annually | 2015-03-01 | N/A
8 | Duty to Maintain an Asset Register | Establish and maintain a register of structures, including ownership which are believed to have a significant effect on a local flood risk. | Borough-wide | High | - | - | £10K | Meeting obligations under the Floods and Water Management Act. Improved understanding of local flood risk mechanisms and asset importance | LB only | Short | 2012 | Long | FWMA / FRR | Register is prepared. We have Floodstation which is populated. | LB Tower Hamlets | Transport / Highways | Environment Agency | LoDEG | No | Annually | 2015-03-01 | N/A
9 | Investigation and recording of flood incidents in a consistent maner | Investigate flooding incidents (where other risk management authorities do not respond and to the extent that it considers necessary or appropriate) to identify which authorities have relevant functions to deal with the flood and whether each of them intends to respond. Use the standard data capture form developed as part of Drain London for recording | Borough-wide | High | £20K- £50K | - | - | Meeting obligations under the Floods and Water Management Act. Improved understanding of local flood risk issues. Consistency of data records across Greater London | LB only | Short | 2012 | Long | FWMA / FRR | Proforma is prepared and a few entries have been made. These are recorded on GIS. | LB Tower Hamlets | Transport / Highways | Drain London |  | No | Annually | 2015-03-01 | N/A
10 | Sustainable Drainage - LLFAs must establish a SuDS Approval Body (SAB) | SAB to potentially include representatives from Transport & Highways, Spatial Planning, Parks and Open Spaces. Refer to national guidance when available | Borough-wide | High | - | - | TBC | Meeting obligations under the Floods and Water Management Act. Long term implementation of sustainable flood risk management. | LB only | Short | 2012 | Long | FWMA / FRR | The SuDS guidance was completed October 2014 and will be posted on the web. | LB Tower Hamlets | Transport / Highways | Group 4 | UEL LBN | No | Annually | 2015-03-01 | N/A
11 | Ensure drainage systems are operating at capacity across the borough - maintenance of gullies | Review existing gully clearance/ maintenance schedules | Borough-wide | High | - | - | £200k p.a | Flooding isn't exacerbated | LB only | Short | 2011 | 1 year | FMA | we have a cyclical gully cleansing programme, together with arrangements for unscheduled cleans of blocked gullies, and repairs of damaged gullies and cover. | LB Tower Hamlets | Transport / Highways | Thames Water |  | No | Annually | 2015-03-01 | N/A |  | 12
12 | Installation of additional road gullies or reprofile surface to remove any standing water on carriageways across the borough | As part of highways improvement and maintenance programmes, include provision of additional gullies or reprofiling surface where feasible. Consultation with Thames Water may be required. | Borough-wide | Medium | - | Unknown at present | - | Reduction in the probability of flooding | LB only | Short | 2011 | Ongoing | FMA | Embedded as part of standard practice as and when problems occur | LB Tower Hamlets | Transport / Highways | Thames Water |  | No | Annually | 2015-03-01 | N/A |  | 11
13 | Determine whether current emergency response to borough-wide surface water flooding are appropriate | Review our response and ensure that in the event of a flood emergency people are relocated to somewhere safe and dry, and that we can contact as necessary | Borough-wide | High | - | - | - | Residents willl be safe in a flood emergency | LB only | Short | 2011 | 1 year | I / F / D | we have established that the flood level if there was no flood barrier correlates to flood zones 2 & 3. EP are aware that the places of refuge need to be outside this zone . EP have arrangement with EA to meet and ensure MAFP is included | LB Tower Hamlets | Emergency Planning / Civil Contingencies | Local Resilience Forum | TfL, Network Rail | No | Annually | 2015-03-01 | N/A
14 | In Local Flood Risk Zones use SWMP mapped outputs to require developers to ensure development will remain safe and will not increase risk to others, where necessary supported by more detailed integrated hydraulic modelling. | Development Control Policy | All Local Flood Risk Zones across the borough | High | - | - | - | Mid-long term reduction in the consequences of flooding | Private developer | Short | 2012 | LDF Plan Period | Policy |  | LB Tower Hamlets | Development Control | Environment Agency |  | No | Annually | 2013-06-01 | N/A
15 | Developments in critical drainage areas (incl. new development in the Millennium Quarter Regeneration area and Lea Valley Regeneration areas) to contribute financially to measures to reduce surface water flood risk in the CDA. | Section 106, Community Infrastructure Levy, Development Control Policy | All CDAs across the borough | High | - | - | - | Mid-long term reduction in the probability of flooding | Private developer | Short | 2012 | LDF Plan Period | Policy | Manmohan to ask GIS to input SWMP outputs onto Council's public and internal GIS systems. Manmohan to include in Guidance document the requirment for applicants to check this GIS. | LB Tower Hamlets | Development Control | Environment Agency |  | No | Annually | 2013-06-01 | N/A
16 | Developments across the borough to include SUDS measures, resulting in a net improvement in water quantity or quality discharging to sewer compared to existing situation. | Development Control Review and Monitoring of policy implementation | Borough-wide | High | - | - | - | Mid-long term reduce in flood risk and improvement in water quality | Private developer | Short | 2012 | LDF Plan Period | Policy | Requirement is included in Draft SuDS guidance | LB Tower Hamlets | Spatial Planning | Environment Agency |  | No | Annually | 2013-06-01 | N/A
17 | Developments across the borough greater than 0.5 hectares to reduce runoff from site to greenfield runoff rates. | Development Control Review and Monitoring of policy implementation | Borough-wide | High | - | - | - | Mid-long term reduction in the probability of flooding | Private developer | Short | 2012 | LDF Plan Period | Policy | Requirement is included in Draft SuDS guidance | LB Tower Hamlets | Development Control | Environment Agency |  | No | Annually | 2013-06-01 | N/A |  | 18
18 | Developments in Critical Drainage Areas to reduce runoff to predevelopment greenfield runoff rates | Development Control Review and Monitoring of policy implementation | All CDAs across the borough | High | - | - | - | Mid-long term reduction in the probability of flooding | Private developer | Short | 2012 | LDF Plan Period | Policy | Requirement is included in Draft SuDS guidance | LB Tower Hamlets | Development Control | Environment Agency |  | No | Annually | 2013-06-01 | N/A |  | 17
19 | Seek to include SUDS retrofitting policies to enhance or replace conventional drainage systems in LFRZs, or elsewhere as opportunities arise e.g. refurbishment projects | Development Control Review and Monitoring of policy implementation | Borough-wide | High | - | - | - | Mid-long term reduce in flood risk and improvement in water quality | Private developer | Short | 2012 | LDF Plan Period | Policy | Requirement is included in Draft SuDS guidance | LB Tower Hamlets | Development Control | Environment Agency |  | No | Annually | 2013-06-01 | N/A
20 | Seek opportunities within all Masterplans and Area Action Plans to integrate fluvial and surface water flood risk reduction measures | Development Control Review and Monitoring of policy implementation | All Masterplans and Area Action Plans | High | - | - | - | Mid-long term reduce in flood risk and improvement in water quality | Private developer | Short | 2012 | LDF Plan Period | Policy | This should happen naturally anyway, not really for applicants - more for our own planners to be briefed upon. | LB Tower Hamlets | Spatial Planning | Environment Agency |  | No | Annually | 2013-06-01 | N/A
21 | Introduce SuDS into public highways, parks and other areas | Determine highways and other areas within the Borough which are appropriate for rain gardens, treepits and other green areas and work with partners to deliver | Borough-wide | Medium |  | - | - | Greens the area, supports wildlife, reduces discharge into sewers, improves air quality. | LB only | Medium | 2012 | plan period | I / F / D | We have SuDS in Bethnal Green Road, Derbyshire St pocket park and Grundy Street. Further inWeavers Woods, Westferry Road and Monier road area are in progress. More are being planned | LB Tower Hamlets | Transport / Highways | Our colleagues | Housing providers | No | Annually | 2014-06-01 | N/A
22 | Separation of combined sewers by riverside | As new development is borough forward by riverside, ensure local sewers serving the site are separated as part of development proposals and surface water discharged into river | Borough-wide | Medium | - | - | - | Long term reduction in flood risk and pollution. Cheaper to separate sewers as part of regeneration than retrofitting into existing built environment. | Private developer | Short | 2012 | Plan period | Policy |  | LB Tower Hamlets | Development Control | Thames Water | Environment Agency | Yes. Water Framework Directive | Annually | 2015-03-01 | All CDAs
23 | Ensure that the providers of transport infrastructure within the borough are meeting their statutory obligations | Meet with Network Rail and TfL to discuss the overall resilience of service across the borough and record the same. | All TfL and Network rail infrastructre that has been identified as being at risk. | High |  | - | - | Refine understanding of risk to critical infrastructure. Prioritise localised drainage improvements | Network Rail/TfL | Short | 2012 | 1-2 years | C + M | We are awaiting response from TFL re protection of their infrastructure. They were asked Autumn 2012 and have been reminded several times since, most recently May 2013. They have not produced the information | Network Rail/TfL | Transport / Highways | Thames Water, LB Tower Hamlets | Environment Agency | No | Annually | 2015-03-01 | Group4_014, Group4_015, Group4_016, Group4_022, Group4_060, Group4_069, Group4_070, Group4_071, Group4_072
24 | Determine whether services (e.g. power, telecommunications) are resilient to surface water flooding | Meet with critical services providers to discuss the overall resilience of service across the borough | Borough-wide | High |  | - | - | Community resilience to flooding | Service providers | Short | 2012 | 1 year | C + M | Stats were asked formally about what measures they are taking to safeguard their services in Jan 2013. They were reminded in April 2013 and there have been a few responses. We've dischsrged our responsibility now. | Service Providers | Transport / Highways | LB Tower Hamlets | Environment Agency | No | Annually | 2015-03-01 | N/A
25 | Consent to works on ordinary watercourses | Consider proposals for works and determine whether or not they will have a negative impact on flooding | Borough-wide | High |  |  |  | Avoid works to ordinary watercourses inadvertently causing flooding | owner of watercourse | Long | 2012 | plan period | FMA | we have no ordinary water courses | LB Tower Hamlets | Transport / Highways | Owner | Environment Agency | No | Annually | 2015-03-01 | N/A
26 | Resolve flooding in CDA Group4_011 Pleavna and launch Street | Integrated Surface Water modelling of the CDA | CDA specific | High | 15000 |  |  | Reduce the potential flood risk and model flood mitigation scenarios | LBTH only | Short | 2013 | 1 year |  | Was remodelled by Halcrow through the Tier 3 programme of Drain London package, funded by LBTH. Work was completed September 2014 and the CDA is extended with flooding arising from surcharging combined sewers. It has become CDA 6 | LB Tower Hamlets | Transport / Highways |  | TWU | No | One off | 2015-03-01 | Group4_011
27 | Resolve flooding in CDA Group4_013 White's Row, Spitalfields | Integrated Surface Water modelling of the CDA | CDA specific | High | [5 empty] | Short | 2013 | 1 year |  | Works completed by City of London, through their integrated modelling showed that there was no risk of flooding in this area. This CDA is gone | LB Tower Hamlets | Transport / Highways |  |  | No |  | 2015-03-01 | Group 4_013 and CoL Group3_006 |  |  | Done by City of London
28 | Resolve flooding in CDA Group4_014 DLR track surrounding Langdon Park | [12 empty] | we're leaving this with TfL | TfL | Transport / Highways |  |  | No |  | 2015-03-01 | Group 4_014
29 | Resolve flooding in CDA Group4_015 Northern approach of the Blackwall Tunnel, South Bromley | [12 empty] | we're leaving this with TfL | TfL | Transport / Highways |  |  | No |  | 2015-03-01 | Group 4_015
30 | Resolve flooding in CDA Group4_016 A12, northern approach to the Blackwall Tunnel in Bow | [12 empty] | we're leaving this with TfL | TfL | Transport / Highways |  |  | No |  | 2015-03-01 | Group 4_016
31 | Resolve flooding in CDA Group4_021 Beaumont Square, Stepney Green | Integrated Surface Water modelling of the CDA | CDA specific | High | 15000 |  |  | Reduce the potential flood risk and model flood mitigation scenarios | LBTH have committed £5,000 with Drain London funding £10,000 | Short | 2013 | 1 year |  | Was remodelled by Halcrow through the Tier 3 programme of Drain London package, funded by LBTH and Drain London. Work was completed in September 2014 and whilst there is a low spot there is no flooding risk in this area and the CDA is removed | LB Tower Hamlets | Transport / Highways |  |  | No | One off | 2015-03-01 | Group 4_021
32 | Resolve flooding in CDA Group4_022 Intersection of A11 and A12 in Bromley by Bow | [12 empty] | we're leaving this with TfL | TfL | Transport / Highways |  |  | No |  | 2015-03-01 | Group 4_022
33 | Resolve flooding in CDA Group4_025 Cordelia, Ricardo and Grundy Street, South Bromley | Integrated Surface Water modelling of the CDA and installation of SuDS in the LFRZ | CDA specific | High | £15,000 for modelling | - | £11,000 SuDS project | Reducing surface runoff in the CDA and also modelling the flood risk to help mitigate the risk. | The SuDS project is mostly funded by Drain London who have committed £8,500. The rest will be from LBTH | Short | 2013 | 1 year |  | Was remodelled by Halcrow through the Tier 3 programme of Drain London package, funded by LBTH and Drain London. Work was completed in September 2014 and whilst there is a low spot there is no flooding risk in this area and the CDA is removed. SuDS have been installed on the street funded by Drain London. | LB Tower Hamlets | Transport / Highways |  |  | No | One off | 2015-03-01 | Group 4_025
34 | Resolve flooding in CDA Group4_060 Whitechapel Tube station, Whitechapel | [12 empty] | we're leaving this with TfL | TfL | Transport / Highways |  |  | No |  | 2015-03-01 | Group 4_060
35 | Resolve flooding in CDA Group4_069 A1261 Aspen Way Tunnel, East India | [12 empty] | we're leaving this with TfL | TfL | Transport / Highways |  |  | No |  | 2015-03-01 | Group 4_069
36 | Resolve flooding in CDA Group4_070 B125 Abbot Road underpass beneath A12, South Bromley | [12 empty] | we're leaving this with TfL | TfL | Transport / Highways |  |  | No |  | 2015-03-01 | Group 4_070
37 | Resolve flooding in CDA Group4_071 Limehouse Link Tunnel entrance, Poplar | [12 empty] | we're leaving this with TfL | TfL | Transport / Highways |  |  | No |  | 2015-03-01 | Group 4_071
38 | Resolve flooding in CDA Group4_072 London Overground tracks between Shoreditch and Shadwell, Whitechapel | [12 empty] | we're leaving this with TfL | TfL | Transport / Highways |  |  | No |  | 2015-03-01 | Group 4_072
39 | Resolve flooding in CDA Group4_074 Tredegar Road between Cardigan and Parnell Roads in Bow | Integrated Surface Water Modelling of the CDA | CDA specific | High | 15000 |  |  | Reduce the potential flood risk and model flood mitigation scenarios | LBTH only | short | 2013 | 1 year |  | Was remodelled by Halcrow through the Tier 3 programme of Drain London package, funded by LBTH and Drain London. Work was completed in September 2014 and whilst there is a low spot the modelling showed no flood risk. The road did flood in September 2014 and this is under investigation and is thought to have been caused by a blocked sewer. | LB Tower Hamlets | Transport / Highways |  |  | No | One off | 2015-03-01 | Group4_074
40 | protect water bodies | enusre that we don’t impair the curent or future quality of the water bodies in LBTH | Wapping Woods & docks | [9 empty] | FRR | No action as such, but we should keep a watch on this. | LB Tower Hamlets | Transport / Highways |  |  | Yes |  | 2015-03-01
41 | Address potential flooding identified by remodelling work carried out by Halcrow. | look at output and see if there are any areas highlighted that have not been picked up by the Drain London work so far. | area specific | High | staff time only for now |  |  | Reduce the potential flood risk and model flood mitigation scenarios | EA, FDGiA | short | 2014 | 2013-12-06 | FWMA / FRR | The output is showing that two new CDAs need to be added in Isle of Dogs arising from surcharging combined sewers, one new one in the Abbotts Road estate and one existing CDA in Isle of Dogs is extended. These will be added to the SWMP Action Plan | LB Tower Hamlets | Transport / Highways |  |  | Yes | One off | 2014-07-01
updated 201113 RS
Note on A1: Unique ID for action (created on an individual borough basis)
Note on B2: Describe action to be taken
Note on C2: Described how the action should be taken
Note on D2: Street names or post code districts
Note on E1: Determined in consultation with LB Rep.
Note on F2: Estimated investigation costs - use 10% of capital cost or better estimate if available
Note on G2: Estimated capital cost using Prioritisation Matrix unit costs where available. ROUNDED to 2 Significant figures.
Note on H2: Use this field for costs unable to be classified under investigation or capital (e.g. ongoing maintenance if known). Include commentary summarising cost details
Note on I1: Free text description of benefits of specific action.
Note on J1: Summarise potential funding sources and/or mechanisms
Note on K2: Short - Within 1 year Medium - 1 year to 5 years Long - More than 5 years
Note on L2: Approximate start date - format can be determined in consultation with LB representative. Suggest MMM-YYYY or YYYY format.
Note on M2: Estimated action duration - populate with commentary as appropriate
Note on N1: Refer Guidance Note
Note on O1: Free text
Note on P2: State organisation responsible for leading action
Note on Q2: IF the LLFA is the lead organisation - state the sector most likely to take the lead role.
Note on R2: Organisation responsible for supporting the lead organisation (if any)
Note on S1: List other stakeholders who should be involved with action
Note on T1: Note connection to EU Directives or Legislation as required - Water Framework Directive / Floods Directive / Habitats Directive
Note on U2: State frequency of review for action - e.g. monthly / quarterly/ yearly
Note on V2: State next review date based on current date and review frequency
Note on W2: List related CDA ID - for linking to CDA GIS File
Note on X2: State Policy Area ID for linking to Policy Area GIS File
Note on Y2: List ID's of related actions within this action plan
Note on Z2: List related actions from neighbouring Borough action plans (state Borough Name and Action ID)