Corporate Peer Challenge – May 2024

Progress Update Report

28/05/24

**CORPORATE PEER CHALLENGE ACTION PLAN – PROGRESS UPDATE**

The below table contains an overview of all actions and the corresponding latest progress update.

Where available, actions have been RAG-rated.

* + A **Red** RAG-rating denotes that the target date for completion is at serious risk of being missed.
  + An **Amber** RAG-rating denotes that a target date for completion may be at risk of being missed.
  + A **Green** RAG-rating denotes that the action is on track to be completed by the target date.
  + A **Grey** colour fill denotes that the action has been completed.

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **Recommendation** | **No.** | **Action** | **Senior Responsible Officer** | **Target Date for Completion** | **Progress Update** | **RAG** | **Reasons and Mitigating Action** |
| **Recommendation 1: Strategic Vision**  Develop a more comprehensive long-term strategic vision for the borough and the council which is co-produced with the community. | **1.1** | The Mayor will set out, agree and publish a long-term Strategic Vision developed with the input and engagement of the community. The Strategic Vision will inform a Strategic Plan refresh, the Workforce Strategy and the Council will revisit the MTFS to ensure alignment. | Acting Director SIT | Oct-24 | **Previous Update:** Project team has been set up and brief agreed.  SIT is supporting the Mayor’s Office and the Mayor in developing the vision statement.  **Latest Update:** The Mayor’s office is linking development of the vision with other planned community engagement activities to finalise the engagement plan. The delivery date has been reappraised in the light of this work to facilitate more time for community engagement. |  |  |
| **Recommendation 1: Strategic Vision**  Develop a more comprehensive long-term strategic vision for the borough and the council which is co-produced with the community. | **1.2** | The Council will ensure that its strategic plan and subsequent delivery plans are aligned to the long term strategic vision building in regular monitoring and reporting arrangements, and reports that are available to the public | Acting Director SIT | Nov-24 | **Previous Update**: Review the Strategic Plan to ensure it aligns with the Mayor’s long term strategic vision for Cabinet sign off in September 2024. This is dependent on the timing of the Mayor’s long term vision statement. See above.  **Latest Update:** This has been pushed back, as it is dependent upon the completion of the Mayor’s long term strategic vision which has been rescheduled to allow more time for community engagement. |  |  |
| **Recommendation 2: Medium Term Financial Strategy**  Develop a MTFS, including the Housing Revenue Account (HRA), which can demonstrate the future financial sustainability of the council, and which is aligned to the long-term strategic vision of the council. | **2.1** | The Council will complete the development of the new Medium Term Financial Strategy | Corporate Director Resources | Jan-24 | Complete - On the 28th of February the MTFS including the budget and HRA was agreed at Full Council. The plan provides for a sustainable position over the medium term removing previous levels of reliance on reserves to fund recurring costs. | **Completed** |  |
| **Recommendation 2: Medium Term Financial Strategy**  Develop a MTFS, including the Housing Revenue Account (HRA), which can demonstrate the future financial sustainability of the council, and which is aligned to the long-term strategic vision of the council. | **2.2** | The Council will review its MTFS at the point that the long-term strategic vision statement for the Borough is completed to ensure that it is fully aligned to it. | Corporate Director Resources | Oct-24 | **Latest Update**: MTFS will be reviewed once the Strategic vision is developed to ensure alignment, any changes would need to happen through the budget setting process. |  |  |
| **Recommendation 2: Medium Term Financial Strategy**  Develop a MTFS, including the Housing Revenue Account (HRA), which can demonstrate the future financial sustainability of the council, and which is aligned to the long-term strategic vision of the council. | **2.3** | The Council shall revisit its scenario planning and modelling for business rate reform impacts to ensure that they are fit for purpose and up to date. | Corporate Director Resources | Mar-24 | Analyse Local has been engaged to assist with forecasting the appeals provisions. LG Futures has provided updated modelling based on the final local government settlement and the Council’s draft NNDR1 return.  The Autumn Statement, 22nd November 2024, is now being considered in our updated MTFS | **Completed** |  |
| **Recommendation 2: Medium Term Financial Strategy**  Develop a MTFS, including the Housing Revenue Account (HRA), which can demonstrate the future financial sustainability of the council, and which is aligned to the long-term strategic vision of the council. | **2.4** | The Council will develop a single narrative about the financial position of the Council which clearly explains to members, officers and partners the rationale for the savings requirement and investments required in services. This will communicate the imperative of delivery for the future financial sustainability of the council | Corporate Director Resources | Mar-24 | Complete, there is a clear single narrative in place for the MTFS. Slide decks have been produced all aligning the same messages targeted to different audiences, For example Back Bench Councillors, All staff, Transformation Advisory Board. | **Completed** |  |
| **Recommendation 2: Medium Term Financial Strategy**  Develop a MTFS, including the Housing Revenue Account (HRA), which can demonstrate the future financial sustainability of the council, and which is aligned to the long-term strategic vision of the council. | **2.5** | The Council will carry out a comprehensive assessment of the impact of insourcing on service capacity that will feed into the MTFS. | Corporate Director Resources | Mar-24 | Growth for leisure insourcing has been included in the MTFS following work on costings. | **Completed** |  |
| **Recommendation 2: Medium Term Financial Strategy**  Develop a MTFS, including the Housing Revenue Account (HRA), which can demonstrate the future financial sustainability of the council, and which is aligned to the long-term strategic vision of the council. | **2.6** | The Council will complete a HRA review which will explore all financial assumptions against the affordability constraints and will also consider the assumed HRA rent increase. | Corporate Director Resources | Mar-24 | The HRA strategy has been to Cabinet on 31st January with an updated HRA budget following input from Savills. This has a sustainable position and an increase in the number of homes being acquired. | **Completed** |  |
| **Recommendation 3: Performance Management**  To assist with the focus on delivery of the council’s priorities, measures should be taken to enhance the existing performance framework, making better use of data to inform decision making and policy development. Consideration should be given to how the impact of decisions and priority areas is captured. | **3.2** | The Council shall complete a review of existing performance management arrangements in place at the Council to ensure clearer, more consistent processes, scrutiny at service level and by CMT and the development of a system which is understood and can be effectively challenged by members. | Acting Director SIT | May-24 | **Previous Update:** Improvements to presentation of performance data complete  Processes and scrutiny strengthened, including additional scrutiny at MAB and Lead Member 121s (complete). Additional review of scrutiny member mentoring underway.  EDITH, a place-based tool to understand distribution of health and health determinants, enabling comparisons within the borough will be deployed in July.  Further improvements to measures, benchmarking, process and accountability planned through Annual Delivery Plan for 24/25 (Cabinet sign off May 24)  **Latest Update:** The Annual Delivery Plan has now secured Cabinet approval incorporating measures that capture the impact of decisions on priority areas.  A Scrutiny improvement plan has been noted and endorsed by Cabinet and suggested actions in it will be the subject of discussion with Overview and Scrutiny as part of their improvement review process.  The Corporate Board arrangements have been rationalised.  A Power BI platform linking spend and performance has been designed and is being rolled out to Directorates. | **Completed** |  |
| **Recommendation 3: Performance Management**  To assist with the focus on delivery of the council’s priorities, measures should be taken to enhance the existing performance framework, making better use of data to inform decision making and policy development. Consideration should be given to how the impact of decisions and priority areas is captured. | **3.3** | The Council will bring forward new project plans for the development of a data lake and will prioritise progress of data tools to enable easier interrogation of health and societal data bases by council staff. | Corporate Director Resources | Jun-24 | **Previous Update**: Senior agreement in place to develop analytics platform, data tools and series of pilot data products.  .   * An Analytics Service has been designed to roll out data tools * A pilot to develop Finance dashboards agreed * EDITH, a place-based tool to understand distribution of health and health determinants, enabling comparisons within the borough will be deployed in July   **Latest Update:** A corporate project has been set up to develop the Council’s data platforms, data strategy and corporate approach to data analytics.  A Power BI tool providing in-depth analysis of real time spend has been developed for managers and is in the process of being linked to performance data.  Go-live for the finance dashboard will be in June 2024. |  |  |
| **Recommendation 3: Performance Management**  To assist with the focus on delivery of the council’s priorities, measures should be taken to enhance the existing performance framework, making better use of data to inform decision making and policy development. Consideration should be given to how the impact of decisions and priority areas is captured. | **3.4** | The Council will review the Council's current strategy and policy landscape to explore the opportunities to simplify it | Acting Director SIT | TBC-24 | **Latest Update**: Part of Strategic Plan Refresh:  Strategic Plan commitments will be re-evaluated against the Mayor’s long term vision statement and adjustments made as necessary. TBC  Draft for consultation TBC  Final Draft and Cabinet Sign off TBC following rescheduling of the Mayors Long Term vision to facilitate community engagement. |  |  |
| **Recommendation 4: Workforce Strategy**  Develop a refreshed workforce strategy to address recruitment and retention challenges. This is particularly important given the current vacancies in key senior management positions and the Mayor’s stated priority of the workforce representing the community.  The Overview & Scrutiny Committee should be given responsibility for overseeing performance against the council’s aim to ensure that its workforce and service provision reflects the diversity of the borough. | **4.1** | The Council will develop a coordinated workforce strategy with a clear plan for recruitment, retention and workforce development with a more consistent approach being adopted across the organisation and linked to the Council's long term strategic vision. | Corporate Director Resources | Aug-24 | **Previous Update**: Elements of the workforce strategy including the pay policy and senior salary review are complete.  Review of recruitment strategy (including recruiting hard to fill posts and recruiting a workforce to reflect the community) will be complete in July 2024  **Latest Update**: A senior interim Resourcing Lead has been engaged (May 24) to review and address recruitment challenges. Backlog of outstanding recruitment will be picked up by a separate Capacity Team. |  |  |
| **Recommendation 4: Workforce Strategy**  Develop a refreshed workforce strategy to address recruitment and retention challenges. This is particularly important given the current vacancies in key senior management positions and the Mayor’s stated priority of the workforce representing the community.  The Overview & Scrutiny Committee should be given responsibility for overseeing performance against the council’s aim to ensure that its workforce and service provision reflects the diversity of the borough. | **4.2** | The Council will complete the recruitment programme for Corporate Directors and Directors | Corporate Director Resources | Jun-24 | **Previous Update**: Appoint CDS, ADS and MO by May, interim arrangements in place until then.  **Latest Update:** CDS and ADS has been recruited. MO interviews will take place on 28th May 2024. An additional post is to be advertised for the Director of Adult Social Care. The full update was delivered to the HR Committee on 16th May 2024. |  |  |
| **Recommendation 4: Workforce Strategy**  Develop a refreshed workforce strategy to address recruitment and retention challenges. This is particularly important given the current vacancies in key senior management positions and the Mayor’s stated priority of the workforce representing the community.  The Overview & Scrutiny Committee should be given responsibility for overseeing performance against the council’s aim to ensure that its workforce and service provision reflects the diversity of the borough. | **4.3** | The Council will continue to develop the new 'workforce to reflect the community' strategy and embed it into the refreshed workforce strategy | Corporate Director Resources | Jul-24 | **Latest Update:** The WFTC Strategy action plan has been drafted and reviewed by CMT and the  review of the Strategy will be complete in April.  The Strategy will be launched in July.  The WFTC strategy will be embedded as a key tenant in the newly developed workforce strategy once developed. |  |  |
| **Recommendation 4: Workforce Strategy**  Develop a refreshed workforce strategy to address recruitment and retention challenges. This is particularly important given the current vacancies in key senior management positions and the Mayor’s stated priority of the workforce representing the community.  The Overview & Scrutiny Committee should be given responsibility for overseeing performance against the council’s aim to ensure that its workforce and service provision reflects the diversity of the borough. | **4.4** | The Council will review the current governance arrangements for the councils Equality, Diversity and Inclusion agenda. As part of this exercise the Mayor will consider the role of the Overview and Scrutiny Committee specific to the delivery of this agenda. | Acting Director SIT | Jun-24 | **Previous Update**: Structural review of Strategy Improvement and Transformation is underway that will include consideration of where the operational responsibility for the Councils Equality, Diversity and Inclusion Agenda lies within the organisation.  A scoping document for the wider review of governance arrangements for the Equality, Diversity and inclusion is being prepared and draft actions will be agreed after consultation with MAB and O&S.  **Latest Update:** A report was presented to HR Committee and Cabinet on 16th May outlining the high-level changes to the structure of the organisation necessary to align it to strategic priorities and the new Target Operating Model. This will facilitate actions necessary to improve the focus and approach to the equalities’ agenda going forward. |  |  |
| **Recommendation 4: Workforce Strategy**  Develop a refreshed workforce strategy to address recruitment and retention challenges. This is particularly important given the current vacancies in key senior management positions and the Mayor’s stated priority of the workforce representing the community.  The Overview & Scrutiny Committee should be given responsibility for overseeing performance against the council’s aim to ensure that its workforce and service provision reflects the diversity of the borough. | **4.5** | Carry out a review of the Council's Pay Policy for hard to recruit and senior positions. | Corporate Director Resources | Mar-24 | The Pay Policy has been produced and was considered at HR Committee and was approved by Full Council in March.  A salary review of senior roles in the organisation has been commissioned a draft report has been received. Consideration is now being given to the implications of the recommendations. | **Completed** |  |
| **Recommendation 4: Workforce Strategy**  Develop a refreshed workforce strategy to address recruitment and retention challenges. This is particularly important given the current vacancies in key senior management positions and the Mayor’s stated priority of the workforce representing the community.  The Overview & Scrutiny Committee should be given responsibility for overseeing performance against the council’s aim to ensure that its workforce and service provision reflects the diversity of the borough. | **4.6** | LOCD to complete a review of the Council's current talent management and associated support programme and establish what more can be done to support staff development. | Corporate Director Resources | Jul-24 | **Previous Update**: Review of current corporate offer and gaps will be shared with CMT in June.  **Latest Update**: Papers on talent management and mentoring will go to RDLT on 18th June 2024 and then to CMT on 25th June 2024. |  |  |
| **Recommendation 5: Mayor’s Office**  Review the roles, functions and deployment of officers within the Mayor’s Office. This should be done to ensure streamlined decision making, removing barriers and duplication elsewhere in the council. The council should also ensure that colleagues remaining in the Mayor’s Office are given training and development opportunities to ensure a wider understanding of the roles and requirements of different services areas. | **5.1** | The Council will undertake a review of the roles, functions and deployment of officers within the Mayor’s Office with particular focus upon speeding up decision making and removing duplication of function where this is provided elsewhere in the Council. | CEO | Jan-24 | A review has been undertaken and Phase 1 of the restructure complete, savings included in MTFS. Further rationalisation is planned as Phase 2.  Additional training and development has been identified and provided to key members of the Mayor’s Office specific to enabling a wider understanding the roles and requirements of different service areas and the operational environment more generally. | **Completed** |  |
| **Recommendation 6: Internal Governance**  Conduct an urgent review of the internal governance arrangements including the board structures to ensure focus on the delivery of priorities, clarity of reporting and clear lines of accountability. This should seek to speed-up decision making, and delegate business-as-usual decisions to an appropriate level. | **6.1** | The Council will complete a review of the Council's internal governance arrangements, board structures and forward planning process to ensure focus on delivery of priorities, clarity of reporting, and clear lines of accountability. | Corporate Director Resources | Jun-24 | **Latest Update**: Internal Audit have completed an in-depth review of the Councils Internal governance arrangements against the Corporate Governance Improvement Plan.  A mapping exercise of all internal boards is complete and subject to review.  The Transformation Governance Boards have been rationalised from 5 to 3.  Proposals to shorten the forward planning process while retaining overall effective governance will come to CMT before implementation in June 24. |  |  |
| **Recommendation 6: Internal Governance**  Conduct an urgent review of the internal governance arrangements including the board structures to ensure focus on the delivery of priorities, clarity of reporting and clear lines of accountability. This should seek to speed-up decision making, and delegate business-as-usual decisions to an appropriate level. | **6.2** | Review of Transformation Board structure to ensure Boards have delegated authority to oversee and support directorates with budget and restructure delivery | Deputy CEO | Feb-24 | Complete – Transformation Boards have been rationalised from 6 boards to 3 to streamline the Council’s governance. | **Completed** |  |
| **Recommendation 6: Internal Governance**  Conduct an urgent review of the internal governance arrangements including the board structures to ensure focus on the delivery of priorities, clarity of reporting and clear lines of accountability. This should seek to speed-up decision making, and delegate business-as-usual decisions to an appropriate level. | **6.3** | Have in place arrangements to avoid delays in the short-term | CEO | Feb-24 | Complete - The Chief Executive over recent months has introduced new controls on services attempting to bring late reports to MAB/Cabinet or changing reporting dates to ensure a smoother planning process. A process has been introduced at CMT to identify outstanding input from the Mayor’s Office to speed up decision making. | **Completed** |  |
| **Recommendation 6: Internal Governance**  Conduct an urgent review of the internal governance arrangements including the board structures to ensure focus on the delivery of priorities, clarity of reporting and clear lines of accountability. This should seek to speed-up decision making, and delegate business-as-usual decisions to an appropriate level. | **6.4** | The Council will review and clarify the Council's processes for decision making. This will include the review and rationalisation of transaction processes for HR | Corporate Director Resources | Aug-24 | **Previous Update**: A proposal for the HR restructure will be reported to the hr committee on the 16th May 2024 as part of the wider corporate centre proposals in keeping with the emerging new target operating model. The date for this has slipped from March as the structural review took slightly longer than anticipated. Work on review of the Councils processes for decision making are also addressed elsewhere in this plan. See 6.1 to 6.3 above.  **Latest Update:** The TOM has been reviewed and revised. The HR high level structural changes were on 16th May. The next phase will work on the detail and consultation with staff. In line with the new TOM, the decision-making process that was formerly conducted centrally, has been devolved to Directorates.  Three new interim HR experts have been appointed and will start work immediately to support the HR transformation and improvement programme. This will include a priority focus on HR transactional processes. |  |  |
| **Recommendation 6: Internal Governance**  Conduct an urgent review of the internal governance arrangements including the board structures to ensure focus on the delivery of priorities, clarity of reporting and clear lines of accountability. This should seek to speed-up decision making, and delegate business-as-usual decisions to an appropriate level. | **6.5** | Comprehensive review of financial regulations and delegations to inform a revised framework on internal controls | Corporate Director Resources | Jul-24 | **Previous Update**: A comprehensive review of our financial regulations and delegation's is being carried out which will inform a revised framework of internal controls. Cipfa have been commissioned to provide independent assurance that proposed changes reflect best practice. Cipfa have agreed the scope and objectives, mapped the current AS IS process and opportunities for improvement. A detailed project plan is under development. The project will be completed in May.  **Latest Update:** Work is progressing, and the procurement element paper will be going to Cabinet on 10th July (with the latest thresholds). |  |  |
| **Recommendation 6: Internal Governance**  Conduct an urgent review of the internal governance arrangements including the board structures to ensure focus on the delivery of priorities, clarity of reporting and clear lines of accountability. This should seek to speed-up decision making, and delegate business-as-usual decisions to an appropriate level. | **6.6** | The Council will ensure that the new external auditors agree to regular meetings between the Chief Executive, Section 151 Officer and the External Auditor. | Corporate Director Resources | Mar-24 | Meeting between existing external auditors (Deloitte) S151 Officer, and CEO took place on 5th October 2023.  New Auditor Ernst & Young currently in process of exchanging disclosures needed to then enable all regular (quarterly) meetings to be scheduled for the coming financial year | **Completed** |  |
| **Recommendation 6: Internal Governance**  Conduct an urgent review of the internal governance arrangements including the board structures to ensure focus on the delivery of priorities, clarity of reporting and clear lines of accountability. This should seek to speed-up decision making, and delegate business-as-usual decisions to an appropriate level. | **6.7** | The Council will ensure the Head of Audit attends meetings between the three statutory officers. | CEO | Dec-23 | Head of Audit now meeting regularly with Chief Executive, S151 Officer, and Monitoring Officer | **Completed** |  |
| **Recommendation 6: Internal Governance**  Conduct an urgent review of the internal governance arrangements including the board structures to ensure focus on the delivery of priorities, clarity of reporting and clear lines of accountability. This should seek to speed-up decision making, and delegate business-as-usual decisions to an appropriate level. | **6.8** | The Council will report progress on the delivery of the LGA Corporate Peer Challenge Action Plan to the Transformation Advisory Board on a regular basis | Acting Director SIT | Ongoing | Regular engagement taking place with TAB | **Completed** |  |
| **Recommendation 7: Working with Partners**  To ensure more effective partnership working, the council should consider reviewing current partnership governance arrangements. | **7.1** | Create a Partnership Task and Finish Group to review partnership arrangements to ensure a more strategic approach to partnership working, that streamlines governance arrangements and improves accountability. Ensure the Terms of Reference of the Partnership Task and Finish Group specifically develop actions to support these outcomes. | Acting Director SIT | Apr-24 | A partnership Task and Finish Group has been established in October 2023 to take forward strategic review of partnership arrangements.  Findings from the review have been presented back to the Partnership Executive Group  Final report and recommendations coming to CMT by end of March. | **Completed** |  |
| **Recommendation 7: Working with Partners**  To ensure more effective partnership working, the council should consider reviewing current partnership governance arrangements. | **7.2** | Continue to strengthen the Integrated Care partnership to deliver our core priorities and engage with the Integrated Care Board and wider North East London system on what responsibilities and resources can be further devolved to the local level. | Corporate Director Health and Social Care |  | Review underway for Tower Hamlets Together Board arrangements and look to integrate with Health & Wellbeing Board incorporating if possible the formal place-based Committee for the ICB  Review of the Better Care Fund underway, will implement any changes for the 2025/26 financial year. | **Completed** |  |
| **Recommendation 7: Working with Partners**  To ensure more effective partnership working, the council should consider reviewing current partnership governance arrangements. | **7.3** | The Council will further improve the opportunity for strategic conversations with business partnerships and will ensure that the Growth and Economic Development Partnership reviews existing opportunities with a view to enhancing them. | Corporate Director Housing and Regeneration | Review Complete, implementation April | The GED Partnership has been reviewed using the King’s Fund Reflective Learning Framework, as part of the Council’s Partnership Plan 2023-28. The key findings of this review will be implemented by April 25.  GED has delivered a series of 4 themed business breakfast events to engage local businesses, both SME’s and Corporates. Through these events, we have engaged with over 270 SMEs and third sector organisations along with 63 corporate representatives. Due to the success of the programme, GED are seeking further s106 funds to deliver a new programme of events in 24/25, the themes of which will be based on feedback from local businesses. | **Completed** |  |
| **Recommendation 7: Working with Partners**  To ensure more effective partnership working, the council should consider reviewing current partnership governance arrangements. | **7.4** | There are a number of commitments to work with developers and partners to deliver on housing supply ambitions in the ADP including:   * An operational fast track planning service using dedicated resources for Major housing schemes to accelerated housing delivery * Go out to market on the second and third phase of Development Agreement sites in order to deliver new homes in priority locations * Work with the GLA to complete first round of unit acquisitions to increase housing supply | Corporate Director Housing and Regeneration | Jun- 24 | **Previous Update**: Underway as part of ADP process. ADP sign off May Cabinet  **Latest Update:** The principle of a Fast Track Premium Planning Service for specific proposals has been agreed and established with a pilot operational model put in place.  Supporting this, recruitment to three principal and/or senior planning roles, to be funded from within P&BC resources, has begun. Initial pilot schemes for the fast track have been identified and one is now active at pre-app stage.  All 3 tranches of the Developer Agreement sites (11 sites in all) have been released to the market and the Selection Questionnaire date for return is the 24th May 2024.  Progress has also been made on the acquisitions programme. An indicative bid has been made to the GLA for the invited amount of 200 homes over two years. The confirmation of funding is expected in June. | **Completed** |  |
| **Recommendation 7: Working with Partners**  To ensure more effective partnership working, the council should consider reviewing current partnership governance arrangements. | **7.5** | In addition to the above mechanisms continue to enhance work with developers and housing providers. | Corporate Director Housing and Regeneration | Aug- 24 | **Previous Update**: The council has held two one off events for developers in recent months in the Town Hall: an event to showcase 12 council owned site that development partners are being sought for to bring forth much needed affordable housing; an event to showcase the HAP estate regeneration scheme which will deliver more than 400 homes.  Tower Hamlets Housing Forum, Development Subgroup regularly meets, with Registered Providers and the GLA attending to drive development forward in the borough.  A strategic discussion with TFL strategic discussion is planned for July on wider strategic partnership opportunities.  **Latest Update**:  Planning  A Developers Forum date has been identified for the 2 July 2024. Attendance is being confirmed but will include a range of development and housing industry representatives active or with ambitions to be active in the borough. The Mayor, the Lead Member and senior management team is also looking to attend.  Affordable Housing  The Affordable Housing team continues to speak to developers and RPs to enable the progression of stalled sites or those experiencing viability issues. This has enabled progress a number of sites across a range of challenges.  THHF  Social Housing Partners continue to work with the Council through THHF Development sub-group to deliver more affordable homes. Representatives from the Planning Team are regular attendees at quarterly sub-group meetings and have been liaising with the forum on the workings of the newly implemented fast track “in principle” pre app process. Consultations continue on the new Local Plan and possible challenges arising. Members have also been looking at how to improve the speed/cost of delivery incorporating sustainability options. |  |  |
| **Recommendation 8: Grant Allocation**  Build on the framework for the Mayor’s Community Grant scheme and introduce a robust process for the Small Grants Fund and the Emergency Grants Fund, demonstrating links to the corporate priorities, ensuring openness and transparency, and reset relationships with the VCS/third sector. Monitoring of the grants programmes should be undertaken in partnership with the VCS/third sector and overseen by Overview and Scrutiny. | **8.1** | The council will review all council administered grant regimes to ensure that they have robust frameworks in place and will introduce a central grants register. | Acting Director SIT | Apr-24 | **Previous Update**: The Corporate Grants Register data capture process has been completed subject to verification from CD’s. Assurance mechanisms are being checked. The register will go live by the end of April.  **Latest Update:** The Corporate Grants Register has gone live**.** | **Completed** |  |
| **Recommendation 8: Grant Allocation**  Build on the framework for the Mayor’s Community Grant scheme and introduce a robust process for the Small Grants Fund and the Emergency Grants Fund, demonstrating links to the corporate priorities, ensuring openness and transparency, and reset relationships with the VCS/third sector. Monitoring of the grants programmes should be undertaken in partnership with the VCS/third sector and overseen by Overview and Scrutiny. | **8.2** | The Council will work with the VCS to refresh the VCS Strategy and Voluntary Sector Compact which sets out how the Council will work with the sector and will use these to build on and improve existing relationships with the sector. | Acting Director SIT | Jul-24 | **Previous Update**: A Voluntary and Community Sector (VCS) Strategy Refresh Steering group is being established which includes Council reps, VCS reps and other public sector reps. The strategy and compact refresh will be complete by November 2024.  Initial engagement has been undertaken with Cooperate (VCS Partnership Board) and at the VCS Summit on 11th Dec 2023.  **Latest Update:** A project steering group has been set up with representatives from different council services who work with the VCS.  An LGA self-assessment framework has been used to identify what we do with the VCS (considering strengths and weaknesses).  Research has been conducted on good practice from other local authorities who work with the VCS and analysing research papers.  99 stakeholders have been consulted from the VCS, public sector partners, and council officers to develop a draft vision and objectives.  During June and July, further consultation will be undertaken with stakeholders to develop the strategy.  The strategy is due to go to Cabinet in January 2025. |  |  |
| **Recommendation 8: Grant Allocation**  Build on the framework for the Mayor’s Community Grant scheme and introduce a robust process for the Small Grants Fund and the Emergency Grants Fund, demonstrating links to the corporate priorities, ensuring openness and transparency, and reset relationships with the VCS/third sector. Monitoring of the grants programmes should be undertaken in partnership with the VCS/third sector and overseen by Overview and Scrutiny. | **8.3** | Quarterly performance reports to Grants Determination Sub Committee and pre-decision scrutiny by OSC. | Acting Director SIT | Ongoing – June 24 | **Previous Update**: The process for agreeing the KPI’s in partnership with the third sector is in place along with  Quarterly performance reporting to the Grants Determination Sub Committee on performance of projects including any remedial actions to address any challenges.  The feasibility for pre-decision Scrutiny by OSC is being looked at.  **Latest Update:** The Executive has been invited to and has now considered current arrangements for pre-decision scrutiny. |  |  |
| **Recommendation 9: Transfer of Property to Third Parties**  Record and formalise Mayoral/member involvement in decision making relating to the transfer of property to third parties; reflecting Mayoral/member oversight in the property and assets policy and procedures document (and developing overarching strategy) Also report decisions in this area to Overview and Scrutiny Committee. | **9.1** | Complete the Council's new property and asset management strategy to bring together all of the different elements relating to policy and procedure into one document. | Corporate Director Housing & Regeneration | Jul-24 | **Previous Update**: Draft Property and Asset Management Strategy has been completed and will be agreed in May. This has moved back from April due to scheduling issues.  This will form part of the update to our financial regulations and review of the delegation of governance and decision making.  **Latest Update:** The Strategic Asset Management Plan has been completed and will be considered at CMT on 11th June. It is planned to proceed to MAB in early July 2024. |  |  |
| **Recommendation 9: Transfer of Property to Third Parties**  Record and formalise Mayoral/member involvement in decision making relating to the transfer of property to third parties; reflecting Mayoral/member oversight in the property and assets policy and procedures document (and developing overarching strategy) Also report decisions in this area to Overview and Scrutiny Committee. | **9.2** | Property and Asset Management will be added to the member induction and learning programme. | CEO | Jan-24 | Property and Asset Management has been added to the member induction and learning programme | **Completed** |  |
| **Recommendation 9: Transfer of Property to Third Parties**  Record and formalise Mayoral/member involvement in decision making relating to the transfer of property to third parties; reflecting Mayoral/member oversight in the property and assets policy and procedures document (and developing overarching strategy) Also report decisions in this area to Overview and Scrutiny Committee. | **9.3** | The Mayor will review the need for existing levels of pre decision oversight. of delegated decision-making authority to officers regarding decisions relating to land and property disposals (up to £250k) and the letting of property to VCS organisations. | Head of Mayor’s Office | Jun-24 | **Latest Update**: These will be reviewed and consolidated as part of the new Property and Asset Strategy |  |  |
| **Recommendation 9: Transfer of Property to Third Parties**  Record and formalise Mayoral/member involvement in decision making relating to the transfer of property to third parties; reflecting Mayoral/member oversight in the property and assets policy and procedures document (and developing overarching strategy) Also report decisions in this area to Overview and Scrutiny Committee. | **9.4** | All mayoral oversight on decision making pathways will be formalised in the form of written process notes. All feedback by the Mayor to Officers will be recorded as part of these processes. | Deputy CEO | Jun-24 | **Latest Update** These will be reviewed and consolidated as part of the new Property and Asset Strategy. |  |  |
| **Recommendation 10: Cabinet Member Responsibilities**  To speed up the pace of decision-making consideration should be given, as part of the constitutional review, to reviewing the delegated responsibilities from the Mayor to both Cabinet Members and officers. | **10.1** | The Mayor will keep delegation of decision-making authority under constant review. | CEO/Monitoring Officer | Ongoing | As has been common in Elected Mayoral authorities, the Mayor has not delegated decision making to Cabinet Members. Cabinet Members though are involved in all relevant decisions and service challenges as they have regular service meetings and they have to be consulted on all relevant cabinet decision making reports. The Mayor will keep this under constant review. New processes are in place to reduce the incidence of delays in the Mayor’s Office. | **Completed** |  |
| **Recommendation 10: Cabinet Member Responsibilities**  To speed up the pace of decision-making consideration should be given, as part of the constitutional review, to reviewing the delegated responsibilities from the Mayor to both Cabinet Members and officers. | **10.2** | The Council will undertake a review of Local Authorities with directly elected Mayors, with a view to establishing both common practice and best practice regarding delegation of authority. | CEO/Monitoring Officer | Apr-24 | The Association of Democratic Services Officers (ADSO) has been commissioned as part of the LBTH Constitution Review to review the constitutions of the other London Mayoral Authorities and a couple of other authorities of interest to see what they had which was different/useful. ADSO reported back at the end of January and made some minor recommendations for consideration that will be considered by the Constitution working group. The Council was not found to be an outlier in terms of its approach. In addition The CEO is leading a project to bring together CEO’s working in a Directly elected mayoral models across the UK in a new group to better enable best practice to be identified and shared. | **Completed** |  |
| **Recommendation 10: Cabinet Member Responsibilities**  To speed up the pace of decision-making consideration should be given, as part of the constitutional review, to reviewing the delegated responsibilities from the Mayor to both Cabinet Members and officers. | **10.3** | The role and responsibilities of cabinet members under existing arrangements will be the subject of further staff communication bulletins and included more specifically in staff inductions. | CEO/Monitoring Officer | Jan-24 | The staff induction programme has been reviewed and we have improved the information we provided around the roles and responsibilities of cabinet members. | **Completed** |  |
| **Recommendation 11: Membership of Committees**  The council should consider best practice in relation to the chairing, membership and cross party working in and of key committees such as Full Council, Overview and Scrutiny and Audit. External training for these committees should also be arranged. | **11.1** | The Council will define current best practice in relation to chairing, membership, and cross party working in and of committees. It will conduct a review of current terms of reference for committees based on best practice including the appointment of women to lead senior political positions within the council. The Mayor will receive recommendations from that review and agree any necessary actions. The Mayors conclusions will be published. | Head of Democratic Services | Sept-24 | **Previous Update**: The Constitution Working Group are reviewing Committee Terms of Reference compared to other authorities and will propose any changes to the General Purposes Committee for consideration.  A review of overview and scrutiny arrangements is underway with a review to it being reported to MAB in April.  **Latest Update:** A Scrutiny Improvement Plan was reported to MAB in May.  An initial review of Committee Terms of Reference compared to other authorities has been completed.  However, proposing changes to the General Purposes Committee for consideration has been moved to September 24. This is due to factors such as Ramadan and losing the MO. |  |  |
| **Recommendation 11: Membership of Committees**  The council should consider best practice in relation to the chairing, membership and cross party working in and of key committees such as Full Council, Overview and Scrutiny and Audit. External training for these committees should also be arranged. | **11.2** | The Council will continue to deliver the current development programme for scrutiny members, and undertake skills audit in order to develop and deliver an improved development programme for scrutiny and for Cabinet members | CEO | Apr-24 | Training is arranged in relation to almost all Council Committees, both during the Member Induction following the election and then either at the start of the year and/or through the year.  The Council commissioned Centre for Governance and Scrutiny to provide training for scrutiny chairs. This has included three 1-2-1 sessions, two group sessions. A skills audit of scrutiny members has also has been undertaken which informs training plan. | **Completed** |  |
| **Recommendation 11: Membership of Committees**  The council should consider best practice in relation to the chairing, membership and cross party working in and of key committees such as Full Council, Overview and Scrutiny and Audit. External training for these committees should also be arranged. | **11.3** | Introduce a cross party working improvement programme in order to encourage cross party working. | Acting Director SIT | Jul-24 | **Previous Update**: Scrutiny Officers are in the process of reviewing cross party working arrangements. On 29th April a session will be held that reviews cross party working with scrutiny members that will be facilitated by the Centre for Governance and Scrutiny. Recommendations emerging from that review session will then be followed up as part of a wider cross party working improvement initiative.  **Latest Update:** The 29th April session with Centre for Governance and Scrutiny has now taken place. |  |  |
| **Recommendation 11: Membership of Committees**  The council should consider best practice in relation to the chairing, membership and cross party working in and of key committees such as Full Council, Overview and Scrutiny and Audit. External training for these committees should also be arranged. | **11.4** | The Constitution Working Group to consider a report on the workings of Cabinet decision making processes that will include the scrutiny process and present a briefing note to the Mayor in relation to their findings. | Head of Democratic Services | Jun-24 | **Previous Update**: The Association of Democratic Services Officers (ADSO) was commissioned as part of our Constitution work to review the constitutions of the other London Mayoral Authorities and a couple of other authorities of interest to see what they had which was different/useful. See 10.2 above. The report will be considered by the Constitution working group at a date to be scheduled.  **Latest Update:** The report has been completed and circulated for Members’ consideration ahead of a meeting on 19th June 2024. |  |  |
| **Recommendation 12: Member Development**  The existing member training and development offer should be strengthened with support initially focussed on Cabinet members and committee chairs. | **12.1** | The existing member development programme for those in senior positions will be further developed to include opportunities of external mentoring. | Head of Democratic Services | Jun-24 | **Previous Update:** Democratic Services are actively exploring external mentoring opportunities to add to the expansive member development programme already in place. This is specific to Cabinet Members and Committee Chairs. ADSO and South East Employers have been contacted to explore the potential for their support in establishing a mentoring programme.  **Latest Update:** ASDO and North West Employers have confirmed their ability to support a mentoring programme. |  |  |
| **Recommendation 13: Diversity**  Given the composition of the ruling administration, consideration should be given to how the voices of women and those from different backgrounds are directly influencing policy through their lived experience. It is recommended that the council actively promote the LGA’s ‘Be a Councillor Campaign’ to promote the opportunity for women and people from underrepresented groups across the borough. | **13.1** | The Council will undertake a review of how the voices of women and those from different backgrounds are and are not directly influencing policy through their lived experiences and develop a plan for removing barriers to this happening. | Acting Director SIT | Aug-24 | **Previous Update**: A Tower Hamlets Women Commission has now been established that will amplify women's voices within the community and feed into the development of recommendations to the Council. Part of its remit will be to examine the extent to which the voices of women from different backgrounds are influencing policy and identifying barriers that prevent this from happening.  A review of the Tower Hamlets equality network is currently underway with a view to strengthen current provision to ensure resident views are incorporated into service design and delivery.  **Latest Update:** The LGA’s ‘Be a Councillor Campaign’ is now being actively promoted by the Council. |  |  |
| **Recommendation 13: Diversity**  Given the composition of the ruling administration, consideration should be given to how the voices of women and those from different backgrounds are directly influencing policy through their lived experience. It is recommended that the council actively promote the LGA’s ‘Be a Councillor Campaign’ to promote the opportunity for women and people from underrepresented groups across the borough. | **13.2** | The Council will run a major promotion campaign targeting women in the community linked to the LGA’s ‘Be a Councillor’ Campaign. All political parties will be encouraged to run their own campaign within their parties to encourage women candidates. | Acting Director SIT | Apr-24 | The ‘Be a Councillor Campaign’ has now been launched and will be supported by a wider campaign strategy for promoting women in public life. | **Completed** |  |
| **Recommendation 13: Diversity**  Given the composition of the ruling administration, consideration should be given to how the voices of women and those from different backgrounds are directly influencing policy through their lived experience. It is recommended that the council actively promote the LGA’s ‘Be a Councillor Campaign’ to promote the opportunity for women and people from underrepresented groups across the borough. | **13.3** | The Council shall review make up of the Council Committees. | Head of Democratic Services/ CEO | Apr-24 | **Previous Update** Additional guidance is being prepared that strengthens the need for gender representation to be considered when deciding upon Committee membership and  roles.  **Latest Update:** The council has reviewed the makeup of its committees. The result has been that a female councillor has been appointed to a scrutiny lead position. An LGBTQ+ member has been appointed to a key chair position. Five female councillors have taken positions on Overview & Scrutiny (joining a female co-optee). | **Completed** |  |
| **Recommendation 13: Diversity**  Given the composition of the ruling administration, consideration should be given to how the voices of women and those from different backgrounds are directly influencing policy through their lived experience. It is recommended that the council actively promote the LGA’s ‘Be a Councillor Campaign’ to promote the opportunity for women and people from underrepresented groups across the borough. | **13.4** | It will consider the feasibility of introducing a Monitored Feedback system for speakers at Council meetings allowing feedback / comment on speaking time fairness and respect. If feasible the Council will introduce it. | Head of Democratic Services/ CEO | Jun-24 | **Latest Update**: The feasibility study has been completed and a feedback system is in the latter stages of being completed. Go live is expected in June. |  |  |
| **Recommendation 13: Diversity**  Given the composition of the ruling administration, consideration should be given to how the voices of women and those from different backgrounds are directly influencing policy through their lived experience. It is recommended that the council actively promote the LGA’s ‘Be a Councillor Campaign’ to promote the opportunity for women and people from underrepresented groups across the borough. | **13.5** | The Council will develop a policy setting out clearly how much time staff led group chairs can take from their substantive duties to develop staff equalities networks. | Corporate Director Resources | Dec-24 | **Latest Update**: Human Resources are reviewing current arrangements. |  |  |
| **Recommendation 13: Diversity**  Given the composition of the ruling administration, consideration should be given to how the voices of women and those from different backgrounds are directly influencing policy through their lived experience. It is recommended that the council actively promote the LGA’s ‘Be a Councillor Campaign’ to promote the opportunity for women and people from underrepresented groups across the borough. | **13.6** | The Council will ensure all network groups have a senior management sponsor.  Establish a regular programme of meetings with sponsors to discuss progress and relevant cross cutting issues.  Establish a feedback system for Staff Chairs of networks to comment on the performance of the Senior Management Sponsor. | Corporate Director Resources / Acting Director SIT | Dec-24 | Complete – new network sponsors confirmed, meeting cycle established and feedback system in place. | **Completed** |  |
| **Recommendation 13: Diversity**  Given the composition of the ruling administration, consideration should be given to how the voices of women and those from different backgrounds are directly influencing policy through their lived experience. It is recommended that the council actively promote the LGA’s ‘Be a Councillor Campaign’ to promote the opportunity for women and people from underrepresented groups across the borough. | **13.7** | Review and rerun staff and member awareness programme. | Head of Democratic Services | TBC-24 | **Previous Update:** Awareness programme timetables are currently being reviewed.  **Latest Update**: Some initial publicity for the programme has begun, including launching a basic website. There were also multiple pop-up banners to advertise this in the entrance lobby to the Town Hall.  A survey is currently being conducted, aimed at women to learn more about whether they are interested or what barriers remain. There is also an in-person event planned in August aimed at women and one during Black History Month to capture underrepresented ethnic groups. |  |  |
| **Recommendation 13: Diversity**  Given the composition of the ruling administration, consideration should be given to how the voices of women and those from different backgrounds are directly influencing policy through their lived experience. It is recommended that the council actively promote the LGA’s ‘Be a Councillor Campaign’ to promote the opportunity for women and people from underrepresented groups across the borough. | **13.8** | To contribute to the LGA call for evidence for Supporting Women and girls to be active. | Corporate Director Communities | Apr-24 | The LBTH submission has been completed. | **Completed** |  |
| **Recommendation 14: Annual governance Statement**  Prepare and publish the Annual Governance Statement. | **14.1** | The Council will secure the necessary outstanding internal approvals and publish the outstanding Annual Governance Statements | Corporate Director Resources | Dec-23 | Completed. Outstanding Annual Governance Statement approved by the Audit Committee on Thursday 19th October 2023. Published on the Council web site. | **Completed** |  |
| **Recommendation 15: Outstanding Accounts**  Outstanding financial accounts going back to 2018/19 need to be resolved with the external auditors as a priority. | **15.1** | The Council will take action to resolve all of the historic outstanding financial accounts going back to 2018/19 | Corporate Director Resources | Jan-24 | Complete | **Completed** |  |
| **Recommendation 16: Organisational Capacity**  Develop the corporate centre so that it is genuinely a strategic enabler and provides the appropriate accurate management data and information to support the transformation of the organisation. | **16.1** | The Council will complete a strategic resource needs assessment covering HR, Procurement, Facilities, Communications, IT addressing additional demand resulting from insourcing. | Corporate Director Resources | Oct-24 | **Previous Update:** Initial recommendations have been proposed by the Corporate Director Resources during Autum 2023; These are being considered as part of a wider structural review of the Resources Directorate.  **Latest Update:** The strategic resource needs assessment for HR and Procurement has been agreed (rest to follow). |  |  |
| **Recommendation 16: Organisational Capacity**  Develop the corporate centre so that it is genuinely a strategic enabler and provides the appropriate accurate management data and information to support the transformation of the organisation. | **16.2** | The Council will produce a revised set of Organisational Health reports/dashboards that will;  · Reflect performance against regulatory targets  · Bring together performance across the Council that is aligned with up-to-date priorities and strategies  · Report from line of business systems or automated reports that does not require substantial manual intervention  · Allow CMT members to interrogate the dashboard outside of the meeting cycle | Acting Director SIT | Jul-24 | **Previous Update:** Requirement gathering starting Feb, expect first presentation of data in July 24  **Latest Update:** The Power BI platform has been developed by the Resources Directorate for senior managers to easily interrogate real time spend and financial performance. Work is underway to link this to key performance indicators.  The delivery plan has been completed which includes the revision of KPIs to ensure alignment with priorities and strategies.  A performance dashboard has been developed for the Transformation Advisory Board (TAB) | **Completed** |  |
| **Recommendation 16: Organisational Capacity**  Develop the corporate centre so that it is genuinely a strategic enabler and provides the appropriate accurate management data and information to support the transformation of the organisation. | **16.3** | The Council will conduct a strategic review of the Procurement function to make it a model of best practice. | Corporate Director Resources | Apr-25 | **Previous Update**: The Council has engaged Lumensol to review its Procurement Service and structure. A Programme Director for Procurement was appointed in April for a 12-month term, tasked with developing a new delivery model that aligns with best practices.  **Latest Update**: Interim Programme director is working on the new processes. TOM agreed at HR Committee on 16th May 2024. |  |  |
| **Recommendation 16: Organisational Capacity**  Develop the corporate centre so that it is genuinely a strategic enabler and provides the appropriate accurate management data and information to support the transformation of the organisation. | **16.4** | The Procurement function of the Council will introduce a standard set of terms and conditions for contract awards. | Corporate Director Resources | Sept-24 | **Previous Update**: We are currently reviewing our procurement procedures and standing orders to align with the new legislation taking effect in October 2024. This review includes examining all our existing policies and procedures and processes. Having completed the initial assessment, we are now in the process of developing more efficient systems in collaboration with the project team, aimed at bringing in a more comprehensive standard set of terms and conditions.  **Latest Update**: This work is progressing with an update scheduled for 10th July 2024. |  |  |
| **Recommendation 16: Organisational Capacity**  Develop the corporate centre so that it is genuinely a strategic enabler and provides the appropriate accurate management data and information to support the transformation of the organisation. | **16.5** | The Council will review and resolve the issue of the Councils Wi-Fi at the Town Hall | Corporate Director Resources | Jun-24 | **Previous Update**: A review of the Wi-fi in the building has been completed and no significant issues identified. However, problems with mobile phone connectivity has been confirmed. A programme of remedial action is now in hand.  **Latest Update**: The Wi-Fi service is being regularly monitored and is reporting consistently good service.  A project to remediate mobile signal issue has engaged a supplier to install signal booster to provide mobile coverage. Supplier is engaging with FM to conduct Hertiage Building survey and plan implementation. | **Completed** |  |
| **Recommendation 16: Organisational Capacity**  Develop the corporate centre so that it is genuinely a strategic enabler and provides the appropriate accurate management data and information to support the transformation of the organisation. | **16.6** | CEO and CMT to consider current relationship standing with the trade unions and agree actions that might further promote better working relationships. | Deputy CEO | Jul-24 | **Previous Update**:  Subject scheduled for discussion at CELT  **Latest Update:** This will be addressed as a priority workstream within the HR improvement programme (currently underway). |  |  |
| **Recommendation 17: Responsiveness**  Review the council wide approach to handling member enquiries, complaints and freedom of information (FOI) requests to ensure less duplication, faster responses and greater efficiency. | **17.1** | The Council will complete a resource review of the Councils FOI, Members Enquiries and Complaints functions. The Council will complete a process review for member enquiries, complaints and FOI requests with a view to improving speed and efficiency. | Deputy CEO | TBC | **Previous Update:**   * FOI Review completed * Mayor enquiries and complaint reviews underway * Scoping for CEO compliance project underway   **Latest Update:** Full improvement plan has been developed. Complaints process review is now completed. |  |  |
| **Recommendation 18: ‘People First’**  Accelerate the ‘People First’ transformation programme and develop a clear narrative ensure a common understanding. (This should be entwined with the development of the strategic vision) | **18.1** | The Council will develop a clear, single narrative around transformation and improvement using the people first initiative to do so. The Council will develop a communications / wider culture change programme to promote a wider council staff identity and help break down silo’s and support senior staff visibility. | Director of Communications | Apr-24 | **Previous Update:** Communications are developing the People First Campaign linking to culture change. Complete by April 24  **Latest Update:** This action has now been completed. The Communications team has developed a clear, single narrative around transformation and improvement through the People First initiative and linking to culture change. This will be launched at the Staff Conference on 11th July 2024 and embedded through the organisation (via Communications). | **Completed** |  |